## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
SPRINT 1 | SPRINT 1 | US-01 | Collect and import workforce employee data | Must | CSV/HR data source | Kavya,Keertana | Completed
SPRINT 1 | SPRINT 1 | US-02 | Validate, clean, and standardize workforce data | Must | US-01 | Sanjay,Santhosini | Completed
SPRINT 1 | SPRINT 1 | US-03 | Design database schema for employee and talent metrics | Must | US-01 | Navya,Tanisha | Completed
SPRINT 1 | SPRINT 1 | US-04 | Build employee data management APIs | Must | US-03 | Gowshika | Completed
SPRINT 2 | SPRINT 2 | US-05 | Calculate workforce KPIs and summary metrics | Must | US-02, US-04 | Santhosini | Completed
SPRINT 2 | SPRINT 2 | US-06 | Implement attrition-risk prediction module | Should | US-02 | Nikhil | Completed
SPRINT 2 | SPRINT 2 | US-07 | Develop talent skill-gap analysis | Should | US-02, US-04 | Keertana | Completed
SPRINT 2 | SPRINT 2 | US-08 | Create executive analytics dashboard | Must | US-05 | Keertana,Navya | Completed
SPRINT 3 | SPRINT 3 | US-09 | Add interactive filters and drill-down views | Should | US-08 | Kavya | Completed
SPRINT 3 | SPRINT 3 | US-10 | Integrate talent insights and recommendations | Should | US-06, US-07 | Nikhil,Kavya | Completed
SPRINT 3 | SPRINT 3 | US-11 | Perform integration, unit testing, and defect fixes | Must | US-04 to US-10 | Santhoshini | Completed
SPRINT 3 | SPRINT 3 | US-12 | Prepare deployment documentation and final review | Could | US-11 | Kavya | Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
Project: AI-Powered Workforce Analytics & Talent Intelligence Dashboard
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 188 | 90.3 | 76.3 | 21.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1–3 TASK BACKLOG (AUG 1 – SEP 6, 2026)
US-01 | T1 | Define workforce data fields and source mapping | 2026-08-01 | 2026-08-01 | Team Member 1 | Analysis | Completed | 4 | Day 1: 4
US-01 | T2 | Create sample employee dataset and import routine | 2026-08-02 | 2026-08-03 | Team Member 1 | Development | Completed | 6 | Day 1: 3; Day 2: 3
US-02 | T3 | Identify missing, duplicate, and invalid records | 2026-08-03 | 2026-08-04 | Team Member 2 | Data Preparation | Completed | 5 | Day 1: 2.5; Day 2: 2.5
US-02 | T4 | Implement data cleaning and standardization rules | 2026-08-05 | 2026-08-06 | Team Member 2 | Development | Completed | 8 | Day 1: 4; Day 2: 4
US-03 | T5 | Design employee and department tables | 2026-08-06 | 2026-08-07 | Team Member 3 | Database | Completed | 6 | Day 1: 3; Day 2: 3
US-03 | T6 | Create KPI and talent metric tables | 2026-08-08 | 2026-08-09 | Team Member 3 | Database | Completed | 5 | Day 1: 2.5; Day 2: 2.5
US-04 | T7 | Create employee CRUD REST endpoints | 2026-08-10 | 2026-08-12 | Team Member 1 | Backend | Completed | 10 | Day 1: 3.3; Day 2: 3.3; Day 3: 3.3
US-04 | T8 | Connect APIs with MySQL and validate responses | 2026-08-13 | 2026-08-14 | Team Member 1 | Integration | Completed | 8 | Day 1: 4; Day 2: 4
US-05 | T9 | Define workforce KPI formulas | 2026-08-15 | 2026-08-15 | Team Member 2 | Analytics | Completed | 4 | Day 1: 4
US-05 | T10 | Implement headcount, retention, and turnover metrics | 2026-08-16 | 2026-08-18 | Team Member 2 | Development | Completed | 10 | Day 1: 3.3; Day 2: 3.3; Day 3: 3.3
US-06 | T11 | Prepare features for attrition-risk model | 2026-08-17 | 2026-08-19 | Team Member 3 | Machine Learning | Completed | 10 | Day 1: 3.3; Day 2: 3.3; Day 3: 3.3
US-06 | T12 | Train and validate baseline prediction model | 2026-08-20 | 2026-08-21 | Team Member 3 | Machine Learning | Completed | 10 | Day 1: 5; Day 2: 5
US-07 | T13 | Map employee skills and required role skills | 2026-08-20 | 2026-08-22 | Team Member 4 | Talent Analytics | Completed | 8 | Day 1: 2.7; Day 2: 2.7; Day 3: 2.7
US-07 | T14 | Implement skill-gap scoring logic | 2026-08-23 | 2026-08-24 | Team Member 4 | Development | Completed | 8 | Day 1: 4; Day 2: 4
US-08 | T15 | Create dashboard layout and KPI cards | 2026-08-22 | 2026-08-24 | Team Member 1 | Frontend | Completed | 8 | Day 1: 2.7; Day 2: 2.7; Day 3: 2.7
US-08 | T16 | Build workforce trend and department charts | 2026-08-25 | 2026-08-27 | Team Member 1 | Frontend | Completed | 10 | Day 1: 3.3; Day 2: 3.3; Day 3: 3.3
US-08 | T17 | Integrate dashboard with analytics APIs | 2026-08-27 | 2026-08-28 | Team Member 1 | Integration | Completed | 8 | Day 1: 4; Day 2: 4
US-09 | T18 | Add department, role, and date filters | 2026-08-29 | 2026-08-30 | Team Member 2 | Frontend | Completed | 8 | Day 1: 4; Day 2: 4
US-09 | T19 | Add drill-down employee and department views | 2026-08-31 | 2026-09-01 | Team Member 2 | Frontend | Completed | 8 | Day 1: 4; Day 2: 4
US-10 | T20 | Generate talent insight summaries | 2026-08-30 | 2026-09-01 | Team Member 3 | AI/Analytics | Completed | 8 | Day 1: 2.7; Day 2: 2.7; Day 3: 2.7
US-10 | T21 | Add actionable workforce recommendations | 2026-09-02 | 2026-09-02 | Team Member 3 | AI/Analytics | Completed | 6 | Day 1: 6
US-11 | T22 | Write unit tests for APIs and KPI services | 2026-09-02 | 2026-09-03 | Team Member 4 | Testing | Completed | 8 | Day 1: 4; Day 2: 4
US-11 | T23 | Execute integration tests and log defects | 2026-09-03 | 2026-09-04 | Team Member 4 | Testing | Completed | 8 | Day 1: 4; Day 2: 4
US-11 | T24 | Fix identified dashboard and API defects | 2026-09-04 | 2026-09-05 | Team Member 1 | Bug Fixing | Completed | 8 | Day 1: 4; Day 2: 4
US-12 | T25 | Prepare deployment and user documentation | 2026-09-05 | 2026-09-06 | Team Member 1 | Documentation | Completed | 6 | Day 1: 3; Day 2: 3
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
SPRINT 1 | Day 1 (01-Aug-2026) | No major impediment | Continued planned development/testing work
SPRINT 1 | Day 2 (02-Aug-2026) | No major impediment | Continued planned development/testing work
SPRINT 1 | Day 3 (03-Aug-2026) | Data/API integration issue identified during development | Reviewed logs, reproduced issue, assigned fix, and retested
SPRINT 1 | Day 4 (04-Aug-2026) | No major impediment | Continued planned development/testing work
SPRINT 1 | Day 5 (05-Aug-2026) | No major impediment | Continued planned development/testing work
SPRINT 1 | Day 6 (06-Aug-2026) | No major impediment | Continued planned development/testing work
SPRINT 1 | Day 7 (07-Aug-2026) | No major impediment | Continued planned development/testing work
SPRINT 1 | Day 8 (08-Aug-2026) | No major impediment | Continued planned development/testing work
SPRINT 1 | Day 9 (09-Aug-2026) | No major impediment | Continued planned development/testing work
SPRINT 1 | Day 10 (10-Aug-2026) | No major impediment | Continued planned development/testing work
SPRINT 1 | Day 11 (11-Aug-2026) | No major impediment | Continued planned development/testing work
SPRINT 1 | Day 12 (12-Aug-2026) | No major impediment | Continued planned development/testing work
SPRINT 1 | Day 13 (13-Aug-2026) | No major impediment | Continued planned development/testing work
SPRINT 1 | Day 14 (14-Aug-2026) | No major impediment | Continued planned development/testing work
SPRINT 2 | Day 15 (15-Aug-2026) | No major impediment | Continued planned development/testing work
SPRINT 2 | Day 16 (16-Aug-2026) | No major impediment | Continued planned development/testing work
SPRINT 2 | Day 17 (17-Aug-2026) | Data/API integration issue identified during development | Reviewed logs, reproduced issue, assigned fix, and retested
SPRINT 2 | Day 18 (18-Aug-2026) | No major impediment | Continued planned development/testing work
SPRINT 2 | Day 19 (19-Aug-2026) | No major impediment | Continued planned development/testing work
SPRINT 2 | Day 20 (20-Aug-2026) | No major impediment | Continued planned development/testing work
SPRINT 2 | Day 21 (21-Aug-2026) | No major impediment | Continued planned development/testing work
SPRINT 2 | Day 22 (22-Aug-2026) | No major impediment | Continued planned development/testing work
SPRINT 2 | Day 23 (23-Aug-2026) | No major impediment | Continued planned development/testing work
SPRINT 2 | Day 24 (24-Aug-2026) | No major impediment | Continued planned development/testing work
SPRINT 2 | Day 25 (25-Aug-2026) | No major impediment | Continued planned development/testing work
SPRINT 2 | Day 26 (26-Aug-2026) | No major impediment | Continued planned development/testing work
SPRINT 2 | Day 27 (27-Aug-2026) | No major impediment | Continued planned development/testing work
SPRINT 2 | Day 28 (28-Aug-2026) | No major impediment | Continued planned development/testing work
SPRINT 3 | Day 29 (29-Aug-2026) | No major impediment | Continued planned development/testing work
SPRINT 3 | Day 30 (30-Aug-2026) | No major impediment | Continued planned development/testing work
SPRINT 3 | Day 31 (31-Aug-2026) | No major impediment | Continued planned development/testing work
SPRINT 3 | Day 32 (01-Sep-2026) | No major impediment | Continued planned development/testing work
SPRINT 3 | Day 33 (02-Sep-2026) | No major impediment | Continued planned development/testing work
SPRINT 3 | Day 34 (03-Sep-2026) | Data/API integration issue identified during development | Reviewed logs, reproduced issue, assigned fix, and retested
SPRINT 3 | Day 35 (04-Sep-2026) | No major impediment | Continued planned development/testing work
SPRINT 3 | Day 36 (05-Sep-2026) | No major impediment | Continued planned development/testing work
SPRINT 3 | Day 37 (06-Sep-2026) | No major impediment | Continued planned development/testing work

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | SPRINT 1 | 2026-08-01 | 2026-08-14 | Team Member 1 | Continue early data validation and API checks | Kavya,Keertana | Keep daily task updates | Add dependency review to sprint planning
2 | SPRINT 2 | 2026-08-15 | 2026-08-28 | Team Member 2 | Continue KPI validation with sample records | Sanjay,Santhosini | Continue peer reviews | Freeze KPI definitions before implementation
3 | SPRINT 3 | 2026-08-29 | 2026-09-06 | Team Member 3 | Continue unit and integration testing | Navya,Tanisha | Keep short daily syncs | Reserve dedicated regression-testing time
4 | [5 empty] | Gowshika
5 | [5 empty] | Santhosini
6 | [5 empty] | Nikhil
7 | [5 empty] | Keertana
Keertana,Navya
Kavya
Nikhil,Kavya
Santhoshini
Kavya